## Sheet1
S/N | CHANGES | FRONTEND DEVELOPMENT | BACKEND DEVELOPMENT | STATUS | BLOCKER | Observations
1 | Implementation of cross-browser support for all sections with calendars | Applicable | Not Applicable | Done |  | The calendar works pefectly for all browser but the date format should be dd-mm-yyyy
2 | Inclusion of debit card request check box on account opening forms (selected accounts) and forwarding of same to the backend | Applicable | Applicable | Pending | The backend should receive request. | The debit card request is also working fine but the delivered email does not contain the new opened account number and account name. Also the debit card request option does not appear for existing customers
3 | Direct presentation of Hope Wallet for 3rd Party account opening form to customer when the menu is clicked | Applicable | Not Applicable | Done |  | Works as desired
4 | Presentation of bulks account opening uploaded files to customer for review and update if necessary | Applicable | Applicable | Pending | Receiving file format from the backend is incorrect.
5 | Redesign of transaction receipt look and feel and presentation | Applicable | Not Applicable | Done |  | The view reciept button does not work when clicked
6 | Retrieval and display of smart card information on bill payments | Applicable | Applicable | Pending | Card Information should be sent from the backend
7 | Information sent to back-office and rendering of energy token on the UI | Applicable | Applicable | Pending | Energy Token data should be sent with the payload from the backend
8 | Debit card request implementation for new and existing customers across applicable account types | Not Applicable | Applicable | Pending
9 | Integration with VAS reseller API | Not Applicable | Applicable | Pending
10 | Validation of uploaded file when opening bulk 3rd party wallet | Not Applicable | Applicable | Pending
11 | Separation of saved beneficiary of Hope bank from beneficiaries of other banks | Not Applicable | Applicable | Pending
12